## Sheet1
ITEM | DECRIPTION | MOSCOW | Date Raised | Status
ICT Clinical Advisor | Need to add the clinicial advisor to the approve workflow. This includes a clinicial group. | Must | 2018-07-03 | New
Contacts or user registration | Need to decide if we will connect to Active Directory or manage iam within the application and have an email verification step | Should | 2018-07-03 | New
Anonymous view | The anon user should only see approved and rejected applications. They should be able to edit anything. If they require an app to be assessed they must login | Must | 2018-07-03 | New
Risk Rating | Need to detemine a risk score for each question in each questionnaire/assessment - this enables a risk rating to be displayed for each assessment/questionnaire | Should | 2018-07-03 | New
Question colouring | Need to colour the questions based on their risk rating | Should | 2018-07-03 | New
3DHB | Each DHB has their own privacy officer and clinicial advisor the application needs to account for this | Must | 2018-07-03 | New
email setup | Need to set-up dev environment for sending emails | Must | 2018-07-03 | New
email for service | Need an 3DHB ICT email address for sending messages | Must | 2018-07-03 | New
domain | Do we need a domain? | Could | 2018-07-03 | New
Business Owner Approval | The business owner should provide approval when the requestor submits the assessment pack | Must | 2018-07-03 | New
IaaS | Productionise the application in the cloud | Could | 2018-07-03 | New
wait till assessments are complete to submit | Need to work out which questionnaires need to be done and when they are then allow a submit | Should | 2018-07-03 | New
contact form | Add a form that emails a request to John | Must | 2018-07-03 | New
guides | Add Johns guides to the Guide Page | Must | 2018-07-03 | New
list for IaaS | Produce a list of services required to move the app to a cloud service | Could | 2018-07-03 | New
test page setup | Create a test page with each user, their email address etc to speed up testing and demonstrations | Could | 2018-07-03 | New
attach files | Allow use to attach files ot the application request | Must | 2018-07-03 | New
Emails | when package is submitted email security officer, privacy officer and clinical advisor after a decision is made email the other decision makers email the outcome of the process to the original requestor | Must | 2018-07-03 | New
letter to DIA | or login to dial specific page or trust domakn | Should | 2018-07-03 | New
IPSG | made up of the hospital manager, Ops manager, Lawyer and CIO (for any DHB) - will be signed off as one, minutes must be attached. | Must | 2018-07-03 | New
raise csm ticket | raise a ticket in Cherwell | Could | 2018-07-03 | New
last changed user and date | make sure the tables have a last changed date and user | Should | 2018-07-03 | New
created date and user | make sure the tables have a created date and user | Should | 2018-07-03 | New
absolute url | add the absolute URL to each model | Could | 2018-07-03 | New
postgres | migrate to database | Could | 2018-07-03 | New
static files | create a space for static files | Should | 2018-07-03 | New
email after ict and privacy and clinical are done | send notifications when the 3 assessors are done. | Could | 2018-07-03 | New
privacy assessment | add all the privacy questions and make it pretty | Should | 2018-07-03 | New | complex
complete ict risk assessment | add all the questions and make it pretty | Should | 2018-07-03 | Complete | complex
special handling | if any of the special handling boxes are ticke then the cloud assessment is no longer neccessary | Must | 2018-07-03 | New
audit log | log all events for transparency | Must | 2018-07-03 | New
guiding principles | governance, self-service, 3DHB, user experience | Must | 2018-07-03 | New
add multi selects and multi type into selects | there is a couple of circumstances where multiple answer could be selected | Must | 2018-07-03 | New
add approval tab to navigation | move the approvals to it's own tab | Must | 2018-07-03 | New